**[](http://intranet.jmt.com/JMT%20Utilities/Forms%20Library/docs/logos/JMTlogo-blue-transp.gif)**

**Mill and Overlay of Westfield Avenue (CR 610) from Tinsman Avenue (MP 1.57) T0 NJ Route 130 (MP 2.92)**

**Pennsauken Township, Camden County, New Jersey**

**Notice to Proceed issued: August 30, 2019**

**Project Completion: May 10, 2020**

**Project Substantial Completion: April 10, 2020.**

**Project start: September 4,2019.**

**Weekly Progress Report**

**9-04-2019 through 9-13-2019**

**Following Construction Activities took place during above period:**

**Concrete Curb and Sidewalk:**

Concrete Vertical Curb and sidewalks were constructed along Westfield Avenue (Eastbound and Westbound) at the following locations:

1. Along Derousse Avenue, East and West
2. Along Sherman Avenue, East and West
3. Along Entrance of MPW, East
4. Along Cover Road, East
5. Along Scovel Avenue, East and West
6. Along Horner Avenue, East and West
7. Along Hillcrest Avenue, East – Curb Only
8. Along Westfield Avenue STA 124+60, RT – across from Derousse Avenue.

**Two Week Look Ahead:**

Construction of Concrete Vertical Curb and Sidewalk will continue along Westfield Avenue.

**Biweekly Progress Meeting:**

Biweekly Progress Meeting 01 was held on September 13, 2019 in the field.

Prepared By:

Gunvant Mistry

Resident Engineer



**Figure 1:** **Concrete Curb and Sidewalk Along Derousse Avenue, West**



**Figure 2: Concrete Curb and Sidewalk Along Derousse Avenue, East**

****



**Figure 3: Concrete Sidewalk along Entrance of MPW, East**

****

**Figure 4: Concrete Curb and Sidewalk along Cove Road, East**

****

**Figure 5: Concrete Curb and Sidewalk along Scovel Avenue, East**



**Figure 6: Concrete Curb and Sidewalk along Scovel Avenue, West**

****

**Figure 7: Concrete Curb and Sidewalk along Sherman Ave, West side**



**Figure 8: Concrete Curb and Sidewalk along Sherman Ave, East**



**Figure 9: Concrete Curb and Sidewalk along Horner Ave, East**



**Figure 10: Concrete Curb and Sidewalk along Horner Ave, West**

******Figure 11: Concrete Curb and Sidewalk Along Hollinshead Ave, East**



**Figure 12: Concrete Curb and Sidewalk along Westfield Ave, STA 124+60 Right**

****