**[](http://intranet.jmt.com/JMT%20Utilities/Forms%20Library/docs/logos/JMTlogo-blue-transp.gif)**

**Mill and Overlay of Westfield Avenue (CR 610) from Tinsman Avenue (MP 1.57) T0 NJ Route 130 (MP 2.92)**

**Pennsauken Township, Camden County, New Jersey**

**Notice to Proceed issued: August 30, 2019**

**Project Completion: May 10, 2020**

**Project Substantial Completion: April 10, 2020.**

**Project start: September 4,2019.**

**Weekly Progress Report**

**9-23-2019 through 9-27-2019**

**Following Construction Activities took place during above period:**

**Concrete Curb and Sidewalk:**

Concrete Vertical Curb and sidewalks were constructed along Westfield Avenue (Eastbound and Westbound) at the following locations:

1. Along Lexington Avenue, West.
2. Topsoil and Asphalt was placed around Curb and Sidewalk.

**Two Week Look Ahead:**

1. Construction of Concrete Vertical Curb and Sidewalk will continue along Westfield Avenue.
2. Construction of Drainage will start.

**Biweekly Progress Meeting:**

Biweekly Progress Meeting 02 was held on September 27, 2019 in the field.

Prepared By:

Gunvant Mistry

Resident Engineer



Concrete Placed Today for Proposed Sidewalk

**Figure 1: Sidewalk completed along Lexington Avenue West**



**Figure 2: Topsoil placement around Curb and Sidewalk at Derousse Avenue, East**



Derousse Avenue

Westfield Avenue

**Figure 3: Asphalt at Sidewalk along Westfield Avenue, RT STA 124+75**



**Figure 4: Topsoil placement along Sidewalk and Curb at Sherman Avenue, East**



**Figure 5: Topsoil and Asphalt along sidewalk and Curb at Sherman Avenue, West**



**Figure 6: Topsoil around sidewalk at Entrance of MWPC, East**



**Figure 7: Topsoil around Curb and Sidewalk along Cove Road, East**



**Figure 8: Topsoil around Curb and Sidewalk along Scovel Ave, West**



**Figure 9:** **Asphalt around Sidewalk along Horner Avenue, East**



**Figure 10: Asphalt around Curb Sidewalk along Horner Avenue, West**