****

**Mill and Overlay of Westfield Avenue (CR 610) from Tinsman Avenue (MP 1.57) T0 NJ Route 130 (MP 2.92)**

**Pennsauken Township, Camden County, New Jersey**

**Notice to Proceed issued: August 30, 2019**

**Project Completion: May 10, 2020**

**Project Substantial Completion: April 10, 2020.**

**Project start: September 4,2019.**

**Weekly Progress Report**

**10-07-2019 through 10-11-2019**

**Following Construction Activities took place during above period:**

**Concrete Curb and Sidewalk:**

1. Contractor was not present at site therefore construction activities were not performed.

**Drainage:**

1. Drainage structures were delivered at site on 10/10/2019.
2. Meeting was held in the field with Drainage installation Team of South State Inc.

**Roadway:**

1. Meeting was held in the field with Steven Squibb (Pennsauken Township Engineer) and locations were marked out along Westfield Avenue within project Limit where there were severe humps or dips

**Two Week Look Ahead:**

1. Construction of Drainage related activities will start from 10/14/2019 and continue for next two weeks.

**Biweekly Progress Meeting:**

1. Biweekly Progress Meeting 03 was held on October 11, 2019 at Pennsauken Township Building.

Prepared By:

Gunvant Mistry

Resident Engineer



**Figure 1: Drainage structures were delivered at site on 10/10/2019.**

****